## Project
project_id | project_name | contract_number | contractor | pmc | chief_engineer | budget | jtd | ntp_date | project_duration_days | substantial_completion | edition_date
TONN-01 | Tonnelle Avenue Bridge Relocation | pkg4 | Conti Civil LLC. | Naik Group | Hamed | 30000000 | 24654293
HOW TO USE THIS TEMPLATE
Tab 1 Project: fill the blue cells with contract metadata.
Tab 2 Risk_Register: fill blue columns. probability/cost/schedule are 1-5 (cost & schedule allow 0).
The 4 score columns (cost, schedule, overall, level) are formulas - do not type in them.
mitigation_log: write your dated update notes here (e.g. "1/13 - did X. 1/27 - did Y.").
The next chat will split this column into a separate Risk_Updates table.
Tab 3 Lookups: rating-scale reference + dropdown source. Do not edit unless scales change.
Add or delete Risk_Register rows freely - 30 is a starting point, ~25-40 is a good range.

## Risk_Register
risk_id | project_id | source_ref | status | risk_category | risk_title | risk_type | probability_score | cost_impact_score | schedule_impact_score | risk_score_cost | risk_score_schedule | risk_score_overall | risk_level | risk_entity | risk_coordinator | mitigation_status | next_review_date | mitigation_log
TONN-CON.01 | TONN-01 | CON.01 | Open | Field Condition | Unidentified subsurface obstructions | Threat | 3 | 4 | 1 | 12 | 3 | 12 | Medium | Contractor | Anton Benedict | Closed |  | 9/12 - Obstruction struck during pier excavation; excavation paused. 10/3 - GPR survey completed; abandoned utility identified as the obstruction. 11/14 - Obstruction removed and excavation resumed. 12/5 - Differing site condition documented; risk closed.
TONN-CON.02 | TONN-01 | CON.02 | Open | Environmental | Area of Concern 20 free product | Threat | 4 | 5 | 3 | 20 | 12 | 20 | High | GDC | Joshua Giron | Open | 2026-05-22 | 9/20 - Free product detected at AOC-20 during environmental monitoring. 10/22 - NJDEP notified; remediation plan submitted. 12/8 - Product recovery underway; volume being quantified. 3/14 - Recovery continuing; extent larger than first estimated. 5/6 - Remediation ongoing; cost exposure under review. 5/23 - Test entry from append script smoke text; ignore this entry.
TONN-CON.03 | TONN-01 | CON.03 | Open | Safety | Bouncing roadplates | Threat | 1 | 1 | 1 | 1 | 1 | 1 | Low | CM | Justin Hwang | Monitoring | 2026-05-22 | 10/5 - Complaints of bouncing road plates over trench; flagged to contractor. 11/2 - Plates re-bedded and pinned; movement reduced. 2/10 - Periodic reinspection added to weekly walk. 4/28 - No movement at latest inspection; monitoring continues.
TONN-CON.04 | TONN-01 | CON.04 | Open | Field Condition | Sinking inlet on the side of northbound lane | Threat | 5 | 1 | 1 | 5 | 5 | 5 | Low | CM | Justin Hwang | Monitoring | 2026-05-22 | 10/10 - Settlement observed at inlet on northbound shoulder; monitoring started. 11/18 - Inlet reset and subbase recompacted. 2/15 - Survey readings stable. 5/2 - Settlement monitoring continuing; no further movement.
TONN-CON.05 | TONN-01 | CON.05 | Open | Field Condition | High rock elevation | Threat | 5 | 5 | 5 | 25 | 25 | 25 | High | Shared | Justin Hwang | Realized | 2026-05-22 | 9/8 - Rock encountered well above boring elevations during excavation. 10/15 - Revised excavation method priced; hoe-ram approach evaluated. 12/3 - Rock removal change order executed. 3/10 - Additional rock quantities realized beyond change order; risk realized.
TONN-CON.06 | TONN-01 | CON.06 | Open | Safety | Loose timber lagging above workers | Threat | 5 | 1 | 1 | 5 | 5 | 5 | Low | Contractor | Anton Benedict | Monitoring | 2026-05-22 | 11/4 - Loose timber lagging identified above work area; zone barricaded. 11/15 - Lagging re-secured and additional walers installed. 2/20 - Lagging added to daily excavation inspection. 5/5 - Condition stable; monitoring continues during ongoing excavation.
TONN-CON.07 | TONN-01 | CON.07 | Open | Construction | Delays due to lack of specialty man power | Threat | 3 | 3 | 3 | 9 | 9 | 9 | Medium | Contractor | Anton Benedict | Monitoring | 2026-05-22 | 9/25 - Specialty crew shortage flagged affecting structural steel work. 10/30 - Contractor secured additional subcontractor support. 2/12 - Crew levels tracked against three-week lookahead. 4/22 - Staffing adequate to date; monitoring continues.
TONN-CON.08 | TONN-01 | CON.08 | Open | Design Change | Reroute watermain to avoid structure | Threat | 1 | 2 | 2 | 2 | 2 | 2 | Low | Designer | Vin Pallypis | Realized | 2026-05-22 | 9/15 - Conflict identified between watermain and new foundation. 10/20 - Watermain reroute design issued by designer. 1/12 - Reroute constructed under change order; risk realized.
TONN-CON.09 | TONN-01 | CON.09 | Open | Safety | Smell of gas from newly installed gas pipe | Threat | 1 | 3 | 3 | 3 | 3 | 3 | Low | GDC | Joshua Giron | Open | 2026-05-22 | 12/2 - Gas odor reported near newly installed service; area cleared and utility notified. 12/3 - Leak located at fitting and repaired by gas utility. 3/8 - Faint odor reported again; utility re-dispatched. 5/4 - Additional monitoring in place; cause under investigation.
TONN-CON.10 | TONN-01 | CON.10 | Open | Construction | Impacts from work occuring on adjacent contracts | Threat | 4 | 3 | 4 | 12 | 16 | 16 | High | GDC | Joshua Giron | Monitoring | 2026-05-22 | 9/30 - Adjacent contract staging conflicting with site access. 11/8 - Interface coordination meeting held; sequencing agreed. 2/20 - Time extension request submitted for access delays. 4/30 - Request under agency review; interface coordination continuing.
TONN-CON.11 | TONN-01 | CON.11 | Open | Political | Government shutdown | Threat | 5 | 5 | 5 | 25 | 25 | 25 | High | GDC | Joshua Giron | Open | 2026-05-22 | 10/1 - Federal shutdown risk raised; funding exposure assessed. 1/15 - Continuing resolution in effect; no work stoppage to date. 4/22 - Shutdown threat ongoing; contingency stoppage plan maintained.
TONN-CON.12 | TONN-01 | CON.12 | Open | Field Condition | Boulders found in soil excavation | Threat | 5 | 3 | 3 | 15 | 15 | 15 | High | Contractor | Anton Benedict | Open | 2026-05-22 | 1/20 - Boulders encountered slowing mass excavation. 3/5 - Quantities tracked; differing site condition notice submitted. 5/2 - Boulder removal ongoing; cost impact being quantified.
TONN-CON.13 | TONN-01 | CON.13 | Open | Field Condition | Heavy rainfall flooding open excavation | Threat | 5 | 2 | 1 | 10 | 5 | 10 | Medium | Contractor | Anton Benedict | Open | 2026-05-22 | 2/10 - Open excavation flooded following storm event. 3/18 - Additional pumps and sump capacity added. 5/6 - Dewatering plan in place; monitoring continuing.
TONN-CON.14 | TONN-01 | CON.14 | Open | Construction | Potential damage to neighboring property curbs | Threat | 4 | 1 | 1 | 4 | 4 | 4 | Low | Contractor | Anton Benedict | Closed |  | 10/12 - Pre-construction curb survey of neighboring property completed. 12/15 - No damage at completion of adjacent work; risk closed.
TONN-CON.15 | TONN-01 | CON.15 | Open | Design Change | Additional requirements for utility poles | Threat | 5 | 2 | 1 | 10 | 5 | 10 | Medium | Designer | Vin Pallypis | Open | 2026-05-22 | 11/10 - Utility company added pole relocation requirements. 2/8 - Revised design for pole relocations under review. 4/28 - Awaiting utility company approval of revised design.
TONN-CON.16 | TONN-01 | CON.16 | Open | Political | Delays caused by President cutting federal funding | Threat | 3 | 5 | 5 | 15 | 15 | 15 | High | Shared | Eric Kautz | Monitoring | 2026-05-22 | 10/5 - Federal funding reduction announced; project exposure reviewed. 1/20 - Funding confirmed for current phase; later phases under watch. 4/15 - No funding impact to date; monitoring continues.
TONN-CON.17 | TONN-01 | CON.17 | Open | Safety | Exceedance of noise levels caused by traffic | Threat | 3 | 1 | 1 | 3 | 3 | 3 | Low | Shared | Eric Kautz | Monitoring | 2026-05-22 | 11/6 - Traffic noise monitoring readings approaching threshold. 2/12 - Readings remain within permitted limits. 5/1 - No exceedance recorded; monitoring continues.
TONN-CON.18 | TONN-01 | CON.18 | Open | Design Change | Additional requirements for bridge overlay | Threat | 3 | 4 | 5 | 12 | 15 | 15 | High | Designer | Vin Pallypis | Open | 2026-05-22 | 11/22 - Agency requested revised bridge overlay specification. 3/3 - Revised overlay design submitted for review. 5/8 - Awaiting agency review of revised overlay.
TONN-CON.19 | TONN-01 | CON.19 | Open | Construction | Coordination issue with utiltiy providers | Threat | 2 | 3 | 3 | 6 | 6 | 6 | Low | Contractor | Anton Benedict | Monitoring | 2026-05-22 | 9/28 - Utility coordination delays flagged across multiple providers. 12/14 - Recurring coordination meetings established. 4/10 - Coordination improving; monitoring continues.
TONN-CON.20 | TONN-01 | CON.20 | Open | Construction | Discovery of additional contaminated materials | Threat | 2 | 2 | 5 | 4 | 10 | 10 | Medium | CM | Eric Kautz | Monitoring | 2026-05-22 | 10/18 - Suspect contaminated material encountered; sampling ordered. 1/25 - Laboratory classification results pending. 4/20 - Disposal plan being finalized; monitoring continues.
TONN-CON.21 | TONN-01 | CON.21 | Open | Design Change | Existing conduit for ITS found in damaged condition | Threat | 5 | 5 | 2 | 25 | 10 | 25 | High | Contractor | Anton Benedict | Monitoring | 2026-05-22 | 11/12 - Existing ITS conduit found damaged during exposure. 2/18 - Replacement conduit design issued. 5/5 - Replacement scope being priced; monitoring continues.
TONN-CON.22 | TONN-01 | CON.22 | Open | Design Change | Bridge pour sequence change | Threat | 5 | 5 | 1 | 25 | 5 | 25 | High | Designer | Yaseen Arshev | Open | 2026-05-22 | 12/6 - Bridge pour sequence revision requested for constructability. 3/12 - Revised pour sequence under designer review. 5/10 - Awaiting approval; cost and schedule impact being assessed.
TONN-CON.23 | TONN-01 | CON.23 | Open | Design Change | Left turn signal out of site has insufficient time | Threat | 4 | 2 | 2 | 8 | 8 | 8 | Medium | Designer | Yaseen Arshev | Monitoring | 2026-05-22 | 11/28 - Left-turn signal timing flagged as insufficient. 3/8 - Revised signal timing proposed to agency. 4/30 - Revised timing under agency review; monitoring continues.
TONN-CON.24 | TONN-01 | CON.24 | Open | Design Change | Additional reinforcement to structure | Threat | 5 | 4 | 2 | 20 | 10 | 20 | High | Designer | Yaseen Arshev | Open | 2026-05-22 | 12/9 - Additional structural reinforcement identified during design review. 3/15 - Revised reinforcement design issued. 5/7 - Cost and schedule impact being quantified.
TONN-CON.25 | TONN-01 | CON.25 | Open | Construction | Dropping temperature before milling | Threat | 2 | 2 | 5 | 4 | 10 | 10 | Medium | Shared | Justin Hwang | Monitoring | 2026-05-22 | 1/8 - Falling temperatures threatening milling and paving window. 3/20 - Paving rescheduled to favorable temperature window. 5/3 - Weather window confirmed; monitoring continues.
TONN-CON.26 | TONN-01 | CON.26 | Open | Financial | Potential overrun for police traffic directors | Threat | 4 | 2 | 1 | 8 | 4 | 8 | Medium | CM | Justin Hwang | Open | 2026-05-22 | 1/14 - Police traffic-director costs trending above estimate. 3/22 - Usage tracked against budget line item. 5/9 - Overrun projected; budget reforecast underway.
TONN-CON.27 | TONN-01 | CON.27 | Open | Safety | Equipment close to live traffic | Threat | 3 | 1 | 1 | 3 | 3 | 3 | Low | Contractor | Anton Benedict | Monitoring | 2026-05-22 | 12/3 - Equipment operating near live travel lanes flagged. 2/22 - Additional barrier protection and spotter assigned. 5/4 - Controls effective; monitoring continues.
TONN-CON.28 | TONN-01 | CON.28 | Open | Financial | Potential overrun of contingency funds | Threat | 3 | 5 | 1 | 15 | 3 | 15 | High | CM | Justin Hwang | Closed |  | 9/22 - Contingency drawdown trending high against budget. 11/30 - Contingency reforecast presented to agency. 1/18 - Additional contingency approved; risk closed.
TONN-CON.29 | TONN-01 | CON.29 | Open | Construction | Adjacent contractor blocking entrance | Threat | 5 | 2 | 3 | 10 | 15 | 15 | High | GDC | Joshua Giron | Open | 2026-05-22 | 2/5 - Adjacent contractor staging blocking site entrance. 3/28 - Interface meeting held; access schedule drafted. 5/11 - Access conflict ongoing; escalated to GDC.
TONN-CON.30 | TONN-01 | CON.30 | Open | Construction | Delays to closeout due to stakeholder signoffs | Threat | 4 | 1 | 1 | 4 | 4 | 4 | Low | CM | Eric Kautz | Open | 2026-05-22 | 3/2 - Closeout signoff dependencies identified across stakeholders. 4/14 - Stakeholder signoff tracker created. 5/12 - Signoffs being pursued; closeout schedule monitored.
TONN-CON.31 | TONN-01 | CON.31 | Open | Construction | Undocumented hazardous material discovered on site | Threat | 1 | 5 | 5 | 5 | 5 | 5 | Low | CM | Eric Kautz | Open | 2026-05-22 | 2/24 - Suspect material uncovered during excavation; work area isolated. 3/19 - Samples sent for laboratory characterization. 5/8 - Results pending; disposal approach being scoped.
TONN-CON.32 | TONN-01 | CON.32 | Open | Construction | Additional subsurface structures found halting excavation | Threat | 1 | 4 | 4 | 4 | 4 | 4 | Low | CM | Eric Kautz | Open | 2026-05-22 | 1/30 - Possible artifacts encountered; excavation paused in affected area. 3/12 - State historic preservation office notified. 5/2 - Awaiting SHPO guidance before resuming.
TONN-CON.33 | TONN-01 | CON.33 | Open | Construction | Temporary shoring damaged by third party | Threat | 1 | 2 | 2 | 2 | 2 | 2 | Low | CM | Eric Kautz | Open | 2026-05-22 | 3/26 - Shoring element struck by third-party vehicle. 4/15 - Damage assessed by engineer; temporary bracing added. 5/9 - Permanent repair being scheduled.
TONN-CON.34 | TONN-01 | CON.34 | Open | Construction | Concrete delivery shortage during critical pour | Threat | 2 | 2 | 3 | 4 | 6 | 6 | Low | CM | Eric Kautz | Open | 2026-05-22 | 2/18 - Supplier flagged limited concrete availability for upcoming pour. 4/3 - Backup supplier being qualified. 5/10 - Pour schedule held pending confirmed supply.
TONN-CON.35 | TONN-01 | CON.35 | Open | Construction | Survey control point disturbed | Threat | 2 | 1 | 1 | 2 | 2 | 2 | Low | GDC | Joshua Giron | Open | 2026-05-22 | 3/5 - Control point found disturbed during layout check. 4/20 - Re-survey ordered to reestablish control. 5/11 - Re-survey in progress.
TONN-CON.36 | TONN-01 | CON.36 | Open | Construction | Permit renewal delay for night work | Threat | 2 | 4 | 2 | 8 | 4 | 8 | Medium | Designer | Yaseen Arshev | Open | 2026-05-22 | 1/22 - Night-work permit renewal application submitted. 3/18 - Agency review extended; renewal not yet issued. 5/6 - Follow-up sent; awaiting issued permit.
TONN-CON.37 | TONN-01 | CON.37 | Open | Construction | Material price escalation on structural steel | Threat | 4 | 3 | 3 | 12 | 12 | 12 | Medium | CM | Justin Hwang | Open | 2026-05-22 | 11/15 - Steel quotes trending above estimate. 1/20 - Escalation confirmed on latest supplier pricing. 3/24 - Cost exposure quantified for reforecast. 5/7 - Escalation ongoing; procurement timing under review.

## Lookups
scale_type | score | label | range_description | category_list | entity_list | status_list
Probability | 1 | Very Low | < 15% | Construction | GDC | Open
Probability | 2 | Low | 16% - 40% | Field Condition | CM | Closed
Probability | 3 | Medium | 41% - 60% | Design Change | Contractor | Monitoring
Probability | 4 | High | 61% - 85% | Safety | Shared | Realized
Probability | 5 | Very High | > 85% | Environmental | Designer
Cost Impact | 1 | Very Low | < $250K | Political
Cost Impact | 2 | Low | $250K - $500K | Financial
Cost Impact | 3 | Medium | $500K - $1M
Cost Impact | 4 | High | $1M - $2M
Cost Impact | 5 | Very High | > $2M
Schedule Impact | 1 | Very Low | < 1 week
Schedule Impact | 2 | Low | 1-2 weeks
Schedule Impact | 3 | Medium | 2-4 weeks
Schedule Impact | 4 | High | 1-2 months
Schedule Impact | 5 | Very High | > 2 months
Risk Level | High | High | Score 15-25
Risk Level | Medium | Medium | Score 8-14
Risk Level | Low | Low | Score 1-7