## Risk_Updates
update_id | risk_id | update_date | update_year | author | note | updated_status | probability_at_update | cost_impact_at_update | schedule_impact_at_update
1 | TONN-CON.05 | 2025-09-08 | 2025 | Justin Hwang | Rock encountered well above boring elevations during excavation. | Open | 5 | 5 | 5
2 | TONN-CON.01 | 2025-09-12 | 2025 | Anton Benedict | Obstruction struck during pier excavation; excavation paused. | Open | 3 | 4 | 1
3 | TONN-CON.08 | 2025-09-15 | 2025 | Vin Pallypis | Conflict identified between watermain and new foundation. | Open | 1 | 2 | 2
4 | TONN-CON.02 | 2025-09-20 | 2025 | Joshua Giron | Free product detected at AOC-20 during environmental monitoring. | Monitoring | 4 | 5 | 3
5 | TONN-CON.28 | 2025-09-22 | 2025 | Justin Hwang | Contingency drawdown trending high against budget. | Open | 3 | 5 | 1
6 | TONN-CON.07 | 2025-09-25 | 2025 | Anton Benedict | Specialty crew shortage flagged affecting structural steel work. | Open | 3 | 3 | 3
7 | TONN-CON.19 | 2025-09-28 | 2025 | Anton Benedict | Utility coordination delays flagged across multiple providers. | Open | 2 | 3 | 3
8 | TONN-CON.10 | 2025-09-30 | 2025 | Joshua Giron | Adjacent contract staging conflicting with site access. | Open | 4 | 3 | 4
9 | TONN-CON.11 | 2025-10-01 | 2025 | Joshua Giron | Federal shutdown risk raised; funding exposure assessed. | Open | 5 | 5 | 5
10 | TONN-CON.01 | 2025-10-03 | 2025 | Anton Benedict | GPR survey completed; abandoned utility identified as the obstruction. | Open
11 | TONN-CON.03 | 2025-10-05 | 2025 | Justin Hwang | Complaints of bouncing road plates over trench; flagged to contractor. | Open | 1 | 1 | 1
12 | TONN-CON.16 | 2025-10-05 | 2025 | Eric Kautz | Federal funding reduction announced; project exposure reviewed. | Open | 3 | 5 | 5
13 | TONN-CON.04 | 2025-10-10 | 2025 | Justin Hwang | Settlement observed at inlet on northbound shoulder; monitoring started. | Monitoring | 5 | 1 | 1
14 | TONN-CON.14 | 2025-10-12 | 2025 | Anton Benedict | Pre-construction curb survey of neighboring property completed. | Open | 4 | 1 | 1
15 | TONN-CON.05 | 2025-10-15 | 2025 | Justin Hwang | Revised excavation method priced; hoe-ram approach evaluated. | Open
16 | TONN-CON.20 | 2025-10-18 | 2025 | Eric Kautz | Suspect contaminated material encountered; sampling ordered. | Open | 2 | 2 | 5
17 | TONN-CON.08 | 2025-10-20 | 2025 | Vin Pallypis | Watermain reroute design issued by designer. | Open
18 | TONN-CON.02 | 2025-10-22 | 2025 | Joshua Giron | NJDEP notified; remediation plan submitted. | Open
19 | TONN-CON.07 | 2025-10-30 | 2025 | Anton Benedict | Contractor secured additional subcontractor support. | Open
20 | TONN-CON.03 | 2025-11-02 | 2025 | Justin Hwang | Plates re-bedded and pinned; movement reduced. | Open
21 | TONN-CON.06 | 2025-11-04 | 2025 | Anton Benedict | Loose timber lagging identified above work area; zone barricaded. | Open | 5 | 1 | 1
22 | TONN-CON.17 | 2025-11-06 | 2025 | Eric Kautz | Traffic noise monitoring readings approaching threshold. | Monitoring | 3 | 1 | 1
23 | TONN-CON.10 | 2025-11-08 | 2025 | Joshua Giron | Interface coordination meeting held; sequencing agreed. | Open
24 | TONN-CON.15 | 2025-11-10 | 2025 | Vin Pallypis | Utility company added pole relocation requirements. | Open | 5 | 2 | 1
25 | TONN-CON.21 | 2025-11-12 | 2025 | Anton Benedict | Existing ITS conduit found damaged during exposure. | Open | 5 | 5 | 2
26 | TONN-CON.01 | 2025-11-14 | 2025 | Anton Benedict | Obstruction removed and excavation resumed. | Open
27 | TONN-CON.06 | 2025-11-15 | 2025 | Anton Benedict | Lagging re-secured and additional walers installed. | Open
28 | TONN-CON.37 | 2025-11-15 | 2025 | Justin Hwang | Steel quotes trending above estimate. | Open | 4 | 3 | 3
29 | TONN-CON.04 | 2025-11-18 | 2025 | Justin Hwang | Inlet reset and subbase recompacted. | Open
30 | TONN-CON.03 | 2025-11-20 | 2025 | Justin Hwang | Reinspected with no movement; risk closed | Open
31 | TONN-CON.18 | 2025-11-22 | 2025 | Vin Pallypis | Agency requested revised bridge overlay specification. | Open | 3 | 4 | 5
32 | TONN-CON.23 | 2025-11-28 | 2025 | Yaseen Arshev | Left-turn signal timing flagged as insufficient. | Open | 4 | 2 | 2
33 | TONN-CON.28 | 2025-11-30 | 2025 | Justin Hwang | Contingency reforecast presented to agency. | Open
34 | TONN-CON.06 | 2025-12-01 | 2025 | Anton Benedict | Cleared by site safety; risk closed | Open
35 | TONN-CON.09 | 2025-12-02 | 2025 | Joshua Giron | Gas odor reported near newly installed service; area cleared and utility notified. | Open | 1 | 3 | 3
36 | TONN-CON.05 | 2025-12-03 | 2025 | Justin Hwang | Rock removal change order executed. | Open
37 | TONN-CON.09 | 2025-12-03 | 2025 | Joshua Giron | Leak located at fitting and repaired by gas utility. | Open
38 | TONN-CON.27 | 2025-12-03 | 2025 | Anton Benedict | Equipment operating near live travel lanes flagged. | Open | 3 | 1 | 1
39 | TONN-CON.01 | 2025-12-05 | 2025 | Anton Benedict | Differing site condition documented; risk closed. | Closed
40 | TONN-CON.22 | 2025-12-06 | 2025 | Yaseen Arshev | Bridge pour sequence revision requested for constructability. | Open | 5 | 5 | 1
41 | TONN-CON.02 | 2025-12-08 | 2025 | Joshua Giron | Product recovery underway; volume being quantified. | Open
42 | TONN-CON.24 | 2025-12-09 | 2025 | Yaseen Arshev | Additional structural reinforcement identified during design review. | Open | 5 | 4 | 2
43 | TONN-CON.07 | 2025-12-10 | 2025 | Anton Benedict | Schedule recovered to baseline; risk closed | Open
44 | TONN-CON.09 | 2025-12-10 | 2025 | Joshua Giron | Air monitoring confirmed clear; risk closed | Monitoring
45 | TONN-CON.04 | 2025-12-12 | 2025 | Justin Hwang | No further settlement observed; risk closed | Open
46 | TONN-CON.19 | 2025-12-14 | 2025 | Anton Benedict | Recurring coordination meetings established. | Open
47 | TONN-CON.14 | 2025-12-15 | 2025 | Anton Benedict | No damage at completion of adjacent work; risk closed. | Closed
48 | TONN-CON.25 | 2026-01-08 | 2026 | Justin Hwang | Falling temperatures threatening milling and paving window. | Open | 2 | 2 | 5
49 | TONN-CON.08 | 2026-01-12 | 2026 | Vin Pallypis | Reroute constructed under change order; risk realized. | Realized | 1 | 2 | 2
50 | TONN-CON.26 | 2026-01-14 | 2026 | Justin Hwang | Police traffic-director costs trending above estimate. | Open | 4 | 2 | 1
51 | TONN-CON.11 | 2026-01-15 | 2026 | Joshua Giron | Continuing resolution in effect; no work stoppage to date. | Open
52 | TONN-CON.28 | 2026-01-18 | 2026 | Justin Hwang | Additional contingency approved; risk closed. | Closed
53 | TONN-CON.12 | 2026-01-20 | 2026 | Anton Benedict | Boulders encountered slowing mass excavation. | Open | 5 | 3 | 3
54 | TONN-CON.16 | 2026-01-20 | 2026 | Eric Kautz | Funding confirmed for current phase; later phases under watch. | Open
55 | TONN-CON.37 | 2026-01-20 | 2026 | Justin Hwang | Escalation confirmed on latest supplier pricing. | Open
56 | TONN-CON.36 | 2026-01-22 | 2026 | Yaseen Arshev | Night-work permit renewal application submitted. | Open | 2 | 4 | 2
57 | TONN-CON.20 | 2026-01-25 | 2026 | Eric Kautz | Laboratory classification results pending. | Open
58 | TONN-CON.32 | 2026-01-30 | 2026 | Eric Kautz | Possible artifacts encountered; excavation paused in affected area. | Open | 1 | 4 | 4
59 | TONN-CON.29 | 2026-02-05 | 2026 | Joshua Giron | Adjacent contractor staging blocking site entrance. | Open | 5 | 2 | 3
60 | TONN-CON.15 | 2026-02-08 | 2026 | Vin Pallypis | Revised design for pole relocations under review. | Monitoring
61 | TONN-CON.03 | 2026-02-10 | 2026 | Justin Hwang | Periodic reinspection added to weekly walk. | Open
62 | TONN-CON.13 | 2026-02-10 | 2026 | Anton Benedict | Open excavation flooded following storm event. | Open | 5 | 2 | 1
63 | TONN-CON.07 | 2026-02-12 | 2026 | Anton Benedict | Crew levels tracked against three-week lookahead. | Open
64 | TONN-CON.17 | 2026-02-12 | 2026 | Eric Kautz | Readings remain within permitted limits. | Open
65 | TONN-CON.02 | 2026-02-15 | 2026 | Joshua Giron | Remediation cost executed via change order; risk realized | Open
66 | TONN-CON.04 | 2026-02-15 | 2026 | Justin Hwang | Survey readings stable. | Open
67 | TONN-CON.21 | 2026-02-18 | 2026 | Anton Benedict | Replacement conduit design issued. | Open
68 | TONN-CON.34 | 2026-02-18 | 2026 | Eric Kautz | Supplier flagged limited concrete availability for upcoming pour. | Open | 2 | 2 | 3
69 | TONN-CON.06 | 2026-02-20 | 2026 | Anton Benedict | Lagging added to daily excavation inspection. | Open
70 | TONN-CON.10 | 2026-02-20 | 2026 | Joshua Giron | Time extension request submitted for access delays. | Open
71 | TONN-CON.27 | 2026-02-22 | 2026 | Anton Benedict | Additional barrier protection and spotter assigned. | Open
72 | TONN-CON.31 | 2026-02-24 | 2026 | Eric Kautz | Suspect material uncovered during excavation; work area isolated. | Open | 1 | 5 | 5
73 | TONN-CON.30 | 2026-03-02 | 2026 | Eric Kautz | Closeout signoff dependencies identified across stakeholders. | Open | 4 | 1 | 1
74 | TONN-CON.18 | 2026-03-03 | 2026 | Vin Pallypis | Revised overlay design submitted for review. | Open
75 | TONN-CON.12 | 2026-03-05 | 2026 | Anton Benedict | Quantities tracked; differing site condition notice submitted. | Open
76 | TONN-CON.35 | 2026-03-05 | 2026 | Joshua Giron | Control point found disturbed during layout check. | Open | 2 | 1 | 1
77 | TONN-CON.09 | 2026-03-08 | 2026 | Joshua Giron | Faint odor reported again; utility re-dispatched. | Open
78 | TONN-CON.23 | 2026-03-08 | 2026 | Yaseen Arshev | Revised signal timing proposed to agency. | Open
79 | TONN-CON.05 | 2026-03-10 | 2026 | Justin Hwang | Additional rock quantities realized beyond change order; risk realized. | Realized | 5 | 5 | 5
80 | TONN-CON.22 | 2026-03-12 | 2026 | Yaseen Arshev | Revised pour sequence under designer review. | Open
81 | TONN-CON.32 | 2026-03-12 | 2026 | Eric Kautz | State historic preservation office notified. | Open
82 | TONN-CON.02 | 2026-03-14 | 2026 | Joshua Giron | Recovery continuing; extent larger than first estimated. | Open
83 | TONN-CON.24 | 2026-03-15 | 2026 | Yaseen Arshev | Revised reinforcement design issued. | Open
84 | TONN-CON.13 | 2026-03-18 | 2026 | Anton Benedict | Additional pumps and sump capacity added. | Open
85 | TONN-CON.36 | 2026-03-18 | 2026 | Yaseen Arshev | Agency review extended; renewal not yet issued. | Open
86 | TONN-CON.31 | 2026-03-19 | 2026 | Eric Kautz | Samples sent for laboratory characterization. | Open
87 | TONN-CON.25 | 2026-03-20 | 2026 | Justin Hwang | Paving rescheduled to favorable temperature window. | Open
88 | TONN-CON.26 | 2026-03-22 | 2026 | Justin Hwang | Usage tracked against budget line item. | Open
89 | TONN-CON.37 | 2026-03-24 | 2026 | Justin Hwang | Cost exposure quantified for reforecast. | Open
90 | TONN-CON.33 | 2026-03-26 | 2026 | Eric Kautz | Shoring element struck by third-party vehicle. | Open | 1 | 2 | 2
91 | TONN-CON.29 | 2026-03-28 | 2026 | Joshua Giron | Interface meeting held; access schedule drafted. | Open
92 | TONN-CON.34 | 2026-04-03 | 2026 | Eric Kautz | Backup supplier being qualified. | Open
93 | TONN-CON.19 | 2026-04-10 | 2026 | Anton Benedict | Coordination improving; monitoring continues. | Monitoring | 1
94 | TONN-CON.30 | 2026-04-14 | 2026 | Eric Kautz | Stakeholder signoff tracker created. | Open
95 | TONN-CON.16 | 2026-04-15 | 2026 | Eric Kautz | No funding impact to date; monitoring continues. | Monitoring
96 | TONN-CON.33 | 2026-04-15 | 2026 | Eric Kautz | Damage assessed by engineer; temporary bracing added. | Open
97 | TONN-CON.20 | 2026-04-20 | 2026 | Eric Kautz | Disposal plan being finalized; monitoring continues. | Monitoring
98 | TONN-CON.35 | 2026-04-20 | 2026 | Joshua Giron | Re-survey ordered to reestablish control. | Open
99 | TONN-CON.07 | 2026-04-22 | 2026 | Anton Benedict | Staffing adequate to date; monitoring continues. | Monitoring
100 | TONN-CON.11 | 2026-04-22 | 2026 | Joshua Giron | Shutdown threat ongoing; contingency stoppage plan maintained. | Open
101 | TONN-CON.03 | 2026-04-28 | 2026 | Justin Hwang | No movement at latest inspection; monitoring continues. | Monitoring
102 | TONN-CON.15 | 2026-04-28 | 2026 | Vin Pallypis | Awaiting utility company approval of revised design. | Open
103 | TONN-CON.10 | 2026-04-30 | 2026 | Joshua Giron | Request under agency review; interface coordination continuing. | Open
104 | TONN-CON.23 | 2026-04-30 | 2026 | Yaseen Arshev | Revised timing under agency review; monitoring continues. | Monitoring
105 | TONN-CON.17 | 2026-05-01 | 2026 | Eric Kautz | No exceedance recorded; monitoring continues. | Monitoring
106 | TONN-CON.04 | 2026-05-02 | 2026 | Justin Hwang | Settlement monitoring continuing; no further movement. | Monitoring
107 | TONN-CON.12 | 2026-05-02 | 2026 | Anton Benedict | Boulder removal ongoing; cost impact being quantified. | Open
108 | TONN-CON.32 | 2026-05-02 | 2026 | Eric Kautz | Awaiting SHPO guidance before resuming. | Open
109 | TONN-CON.25 | 2026-05-03 | 2026 | Justin Hwang | Weather window confirmed; monitoring continues. | Monitoring
110 | TONN-CON.09 | 2026-05-04 | 2026 | Joshua Giron | Additional monitoring in place; cause under investigation. | Monitoring
111 | TONN-CON.27 | 2026-05-04 | 2026 | Anton Benedict | Controls effective; monitoring continues. | Monitoring
112 | TONN-CON.06 | 2026-05-05 | 2026 | Anton Benedict | Condition stable; monitoring continues during ongoing excavation. | Monitoring
113 | TONN-CON.21 | 2026-05-05 | 2026 | Anton Benedict | Replacement scope being priced; monitoring continues. | Monitoring
114 | TONN-CON.02 | 2026-05-06 | 2026 | Joshua Giron | Remediation ongoing; cost exposure under review. | Monitoring
115 | TONN-CON.13 | 2026-05-06 | 2026 | Anton Benedict | Dewatering plan in place; monitoring continuing. | Monitoring
116 | TONN-CON.36 | 2026-05-06 | 2026 | Yaseen Arshev | Follow-up sent; awaiting issued permit. | Open
117 | TONN-CON.24 | 2026-05-07 | 2026 | Yaseen Arshev | Cost and schedule impact being quantified. | Open
118 | TONN-CON.37 | 2026-05-07 | 2026 | Justin Hwang | Escalation ongoing; procurement timing under review. | Monitoring
119 | TONN-CON.18 | 2026-05-08 | 2026 | Vin Pallypis | Awaiting agency review of revised overlay. | Open
120 | TONN-CON.31 | 2026-05-08 | 2026 | Eric Kautz | Results pending; disposal approach being scoped. | Open
121 | TONN-CON.26 | 2026-05-09 | 2026 | Justin Hwang | Overrun projected; budget reforecast underway. | Open
122 | TONN-CON.33 | 2026-05-09 | 2026 | Eric Kautz | Permanent repair being scheduled. | Open
123 | TONN-CON.22 | 2026-05-10 | 2026 | Yaseen Arshev | Awaiting approval; cost and schedule impact being assessed. | Open
124 | TONN-CON.34 | 2026-05-10 | 2026 | Eric Kautz | Pour schedule held pending confirmed supply. | Open
125 | TONN-CON.29 | 2026-05-11 | 2026 | Joshua Giron | Access conflict ongoing; escalated to GDC. | Open
126 | TONN-CON.35 | 2026-05-11 | 2026 | Joshua Giron | Re-survey in progress. | Open
127 | TONN-CON.30 | 2026-05-12 | 2026 | Eric Kautz | Signoffs being pursued; closeout schedule monitored. | Open
128 | TONN-CON.02 | 2026-05-23 | 2026 | Joshua Giron | Test entry from append script smoke text; ignore this entry. | Open